## Sheet1
Tasks | Period in Weeks | Days
|  | August | [7 empty] | September
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
1.0 Design
1.1 Design summary | 2D | bar: August 24 to August 25
1.2 Main Menu Design | 1D | bar: August 26
1.3 Instruction Page Design | bar: August 26
1.4 Game Play Design | 3D | bar: August 27 to August 29
1.5 Result Page Design | 2D | bar: August 30 to August 31
2.0 Content
2.1 Content & Proposal | 2D | bar: August 31 to September 1
3.0 Development
3.1 Software Coding
3.1.1 Main Menu Page | 5D | bar: September 2 to September 6
3.1.2 Instruction Page | 3D | bar: September 6 to September 8
3.1.3 Main Game Page | 6D | bar: September 9 to September 14
3.1.4 Result Page | 2D | bar: September 14 to September 15
3.1.5 Testing | 2D | bar: September 15 to September 16
4.0 Maintenence & Review
4.1 Teacher's feedback | 3D | bar: September 17 to September 19
4.2 Maintenence | 3D | bar: September 20 to September 22
4.3 Submission | 4D | bar: September 23 to September 26